## Sheet1
2017-01-16 | 2017-01-17 | 2017-01-18 | 2017-01-19 | 2017-01-20 | 2017-01-21 | 2017-01-22 | 2017-01-23 | 2017-01-24 | 2017-01-25 | 2017-01-26 | 2017-01-27 | 2017-01-28 | 2017-01-29 | 2017-01-30 | 2017-01-31 | 2017-02-01 | 2017-02-02 | 2017-02-03
Making the game | Making the game | Making the game/documentation | Implementing server/client | Adjusting game to work with server/client | Documentation/writing report |  | Making game playable | Making game playable | Making bonus | Making bonus | Testing | improving code/writing report | Write report/hand in project |  |  | Deadline full grade
Making all methods | Implementing unbeatable AI | Making the documentation of the already finished parts | Making the server and clients (multiple threads) | adjusting code to work with server/client implementation | Finish documentation of game / Begin writing report |  |  |  | GUI | GUI | Testing if everything works as intended | The points on the i placing / writing report about additional features | Write finished report
[9 empty] | Leaderboard | Leaderboard
[9 empty] | Security | Security
[9 empty] | Chat Box | Chat Box